## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Predict Prices of Airlne Tickets |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE |  | Prof. Shital Agrawal |  |  |  |  | DATE | [6 empty] | 2023-04-28
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 | [7 empty] | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-01-13 | 2023-01-18 | 2 | 100% | bar: WEEK 1 M to WEEK 2 M
1.2 | Identifying the functionalities of the Mini Project | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-01-20 | 2023-01-26 | 2 | 100% | bar: WEEK 2 T to WEEK 3 W
1.3 | Discussing the ML Algorithm | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-01-29 | 2023-02-03 | 2 | 100% | bar: WEEK 3 R to WEEK 4 W
1.4 | Designing the Graphical User Interface(GUI) | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-02-04 | 2023-02-10 | 3 | 100% | bar: WEEK 4 R to WEEK 5 F
1.5 | Review1 Presentation | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-02-17 | 2023-02-17 | 1 | 100% | bar: WEEK 5 M to WEEK 6 M
2 | Project Design and Implementation
2.1 | Detail ML Algorithm implementation | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-02-20 | 2023-02-28 | 1 | 100% | bar: WEEK 6 T to WEEK 7 F
2.2 | Integration of GUI with ML Algorithm code | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-03-03 | 2023-03-10 | 1 | 100% | bar: WEEK 7 M to WEEK 8 W
2.3 | Report Writing | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-03-14 | 2023-03-21 | 1 | 100% | bar: WEEK 9 R to WEEK 10 M
2.4 | Review2 Presentation | Dhananjay Phalke Disha Phatta Snehi Ratani | 2023-04-20 | 2023-04-20 | 2 | 100% | bar: WEEK 10 T