## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Cake Town With Recommendation And AI Chatbot | [6 empty] | DEPARTMENT : Information Technology
PROJECT GUIDE: Prof. Charul Singh | [6 empty] | DATE: 20-04-2023
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Dhruvi Haria, Hitesh Sachdev, Aman Yadav, Sushant Waghmare | 13/01/2023 | 18/01/2023 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | Dhruvi Haria, Hitesh Sachdev, Aman Yadav, Sushant Waghmare | 20/1/2023 | 26/1/2023 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
WEEK 3 | Discussing the ML Algorithm Designing the Graphical User Interface (GUI) | Hitesh Sachdev | 29/1/2023 | 2023-10-02 | 1 | 100% | bar: WEEK 2 M to WEEK 3 W
WEEK 4 | Presentation I | Dhruvi Haria, Hitesh Sachdev, Aman Yadav | 17/02/2023 | 17/02/2023 | 0 | 100% | bar: WEEK 2 M to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Detail ML Algorithm implementation | Hitesh Sachdev | 20/2/2023 | 28/2/2023 | 4 | 100% | bar: WEEK 2 M to WEEK 3 R
WEEK 6 | Integration of GUI with ML Algorithm code | Hitesh Sachdev | 2023-03-03 | 2023-10-03 | 2 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Report Writing | Dhruvi Haria | 14/03/2023 | 21/03/2023 | 2 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Presentation II | Dhruvi Haria, Hitesh Sachdev, Aman Yadav, Sushant Waghmare | 20/4/2023 | 20/4/2023 | 0 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 8 M to WEEK 9 F